## Sheet1
Name
Project
Task | Sub Task | Sub Task | Number | Per Task | Estimate | Actual | Units | Amount Assigned | Effciency | Duration
Product Definition
10 | Feature List |  |  |  | 3 |  | 100% | 20% | 50%
| Feature Block Diagram |  |  |  | 2
6 | Behavior Description
2 | Interface List
Architecture
Hardware Block Diagram
Major Signal List
Calculations
Sourcing
Major Component BOM
Pinouts
Current Budget
Engineering Interfaces Management
Architecture Review
Architecture Release
Realization
PCB Design
|  | Library | 10 | 0.25 | 2.5
|  | Schematic Capture | 10 | 0.5 | 5
|  | Layout | 10 | 0.5 | 5
|  | Full BOM | 10 | 0.1 | 1
| Detailed Design |  |  |  | 13.5
Bypassing
Damage Protection
|  | ESD and EMI Protection | 2 | 1
|  | Design for Test | 10 | 0.1
Cable Defintion
Review
Manufacture Package Release
Manufacture
Procurement
Kitting
Fabrication
Assembly
Enclosure Assembly
Cable Assembly
System Assembly
Bring Up
Set Up
Base Line Existing Hardware
Board Induction
Smoke Test
Debug Cycle
Hardware Testing
Firmware Testing
Integration
Testing
Test Setup
Testing the Test
Testing
|  | Hardware Testing | 10 | 2 | 20
|  | Firmware Testing | 6 | 3 | 18
Analysis Development
Analysis
Total |  |  |  |  | 70
Project Management |  |  |  |  | 3.5
Contingency Time |  |  |  |  | 14